## DASHBOARD
AUDIO AMPLIFIER PROJECT CONTROL WORKBOOK
Live project dashboard • Gantt schedule • BOM tracker • Report breakdown • Notes
Project window: 19 Jan 2026 – 20 Feb 2026 (weekdays, 5 weeks)
Overall project status | Not Started |  | Weights (editable) | Engineering | 55% | Normalized | Eng | Rep | BOM
Overall % complete | #VALUE! |  | Sum | Report | 35% | (auto) | 55% | 35% | 10%
Days remaining | 29 |  |  | BOM | 10%
Engineering (Gantt) % | 4.167% |  |  | Total | 100%
Report % | 0%
BOM received % | To Buy
KEY SIGN-OFFS / DELIVERABLES | [6 empty] | Tasks by Status |  |  | BOM Completion
Deliverable | Status | Manual % (optional) | % Complete (auto) | Notes | Planned date |  | Status | Count |  | Category | Count
Final schematic check | Not Started |  | 0% |  | 2026-01-30 |  | Not Started | 23 |  | Received | 5
Final PCB check | Not Started |  | 0% |  | 2026-02-03 |  | In Progress | 0 |  | Not received | 10
PCB soldering check | Not Started |  | 0% |  | 2026-02-09 |  | Done | 1
Final test & measurement | Not Started |  | 0% |  | 2026-02-13 |  | Blocked | 0 |  | Overall | Value
Final audio check (speaker) | Not Started |  | 0% |  | 2026-02-16 |  | Optional | 1 |  | Complete | #VALUE!
Report draft complete | Not Started |  | 0% |  | 2026-02-18 |  |  |  |  | Remaining | #VALUE!
Final report submitted | Not Started |  | 0% |  | 2026-02-20 |  | Progress over time (by planned end date)
[7 empty] | Date | Planned % | Actual %
[7 empty] | 2026-01-19 | 4.167% | 4.167%
[7 empty] | 2026-01-20 | 8.333% | 4.167%
[7 empty] | 2026-01-21 | 12.5% | 4.167%
[7 empty] | 2026-01-22 | 16.67% | 4.167%
[7 empty] | 2026-01-23 | 20.83% | 4.167%
[7 empty] | 2026-01-26 | 25% | 4.167%
[7 empty] | 2026-01-27 | 25% | 4.167%
[7 empty] | 2026-01-28 | 29.17% | 4.167%
[7 empty] | 2026-01-29 | 29.17% | 4.167%
[7 empty] | 2026-01-30 | 33.33% | 4.167%
[7 empty] | 2026-02-02 | 37.5% | 4.167%
[7 empty] | 2026-02-03 | 41.67% | 4.167%
[7 empty] | 2026-02-04 | 45.83% | 4.167%
[7 empty] | 2026-02-05 | 50% | 4.167%
[7 empty] | 2026-02-06 | 50% | 4.167%
[7 empty] | 2026-02-09 | 54.17% | 4.167%
[7 empty] | 2026-02-10 | 58.33% | 4.167%
[7 empty] | 2026-02-11 | 62.5% | 4.167%
[7 empty] | 2026-02-12 | 66.67% | 4.167%
[7 empty] | 2026-02-13 | 75% | 4.167%
[7 empty] | 2026-02-16 | 75% | 4.167%
[7 empty] | 2026-02-17 | 79.17% | 4.167%
[7 empty] | 2026-02-18 | 87.5% | 4.167%
[7 empty] | 2026-02-19 | 95.83% | 4.167%
[7 empty] | 2026-02-20 | 100% | 4.167%

## GANTT
GANTT • ENGINEERING PLAN (WEEKDAYS ONLY)
Update Start/End dates and Status. Bars, progress and dashboard update automatically.
Engineering progress | 4.167% |  |  | (link) | 4.167% |  |  | Status | Count
[8 empty] | Not Started | 23
Timeline (weekdays) | [6 empty] | Mon | In Progress | 0 | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Task | Start | End | Duration (wd) | Status | % Complete | Notes / Evidence | 2026-01-19 | Done | 1899-12-31 | 2026-01-22 | 2026-01-23 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20
Project setup + folder structure | 2026-01-19 | 2026-01-19 | 1 | Done | 100% |  | 1 | Blocked | 0
Read brief + report template + rubric | 2026-01-19 | 2026-01-20 | 2 | Not Started | 0% |  | 1 | Optional | 1
Mobile phone characterisation (440 Hz Vpp vs volume) | 2026-01-20 | 2026-01-21 | 2 | Not Started | 0%
Design calculations (gain + cut-offs + parts rounding) | 2026-01-21 | 2026-01-22 | 2 | Not Started | 0% |  |  |  |  | 1
Stage 1 Proteus simulation (AC sweep + transient) | 2026-01-22 | 2026-01-23 | 2 | Not Started | 0% |  |  |  |  | 1 | 1
Stage 2 power stage simulation (OPA551 load + limits) | 2026-01-23 | 2026-01-26 | 2 | Not Started | 0% | [5 empty] | 1 | 1
Full schematic integration + sanity checks | 2026-01-26 | 2026-01-28 | 3 | Not Started | 0% | [6 empty] | 1 | 1 | 1
Schematic sign-off (final schematic check) | 2026-01-29 | 2026-01-30 | 2 | Not Started | 0% | [9 empty] | 1 | 1
BOM finalised + ordering / picking parts | 2026-01-29 | 2026-02-02 | 3 | Not Started | 0% | [9 empty] | 1 | 1 | 1
Breadboard build (filter stage) | 2026-02-02 | 2026-02-03 | 2 | Not Started | 0% | [11 empty] | 1 | 1
Breadboard build (power stage + speaker) | 2026-02-03 | 2026-02-04 | 2 | Not Started | 0% | [12 empty] | 1 | 1
Breadboard testing (gain + cut-offs + clipping) | 2026-02-04 | 2026-02-05 | 2 | Not Started | 0% | [13 empty] | 1 | 1
PCB layout in Proteus (placement + routing) | 2026-02-05 | 2026-02-09 | 3 | Not Started | 0% | [14 empty] | 1 | 1 | 1
PCB design review / DRC + final PCB check | 2026-02-10 | 2026-02-10 | 1 | Not Started | 0% | [17 empty] | 1
PCB manufacture / wait time (buffer) | 2026-02-10 | 2026-02-11 | 2 | Not Started | 0% | [17 empty] | 1 | 1
Prepare enclosure/baseplate + wiring plan | 2026-02-11 | 2026-02-12 | 2 | Not Started | 0% | [18 empty] | 1 | 1
PCB assembly (soldering) + inspection | 2026-02-12 | 2026-02-13 | 2 | Not Started | 0% | [19 empty] | 1 | 1
PCB soldering check (sign-off) | 2026-02-13 | 2026-02-13 | 1 | Not Started | 0% | [20 empty] | 1
PCB testing + debug | 2026-02-16 | 2026-02-17 | 2 | Not Started | 0% | [21 empty] | 1 | 1
Final test & measurements (plots + screenshots) | 2026-02-17 | 2026-02-18 | 2 | Not Started | 0% | [22 empty] | 1 | 1
Final audio check using speaker | 2026-02-18 | 2026-02-18 | 1 | Not Started | 0% | [23 empty] | 1
Final assembly + cable management | 2026-02-18 | 2026-02-19 | 2 | Not Started | 0% | [23 empty] | 1 | 1
Report writing (merge results + diagrams) | 2026-02-03 | 2026-02-19 | 13 | Not Started | 0% | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Report proof + IEEE refs + appendices | 2026-02-19 | 2026-02-20 | 2 | Not Started | 0% | [24 empty] | 1 | 1
Optional: improve case aesthetics / label controls | 2026-02-16 | 2026-02-20 | 5 | Optional | 0% | [21 empty] | 1 | 1 | 1 | 1 | 1

## BOM
BILL OF MATERIALS (BOM)
Track purchasing + university-provided parts. Status drives completion metrics and charts.
Summary | [8 empty] | BOM Status | Count
Total line items | 13 | [7 empty] | To Get | 6
Received items | 5 | [7 empty] | To Buy | 1
Component / Item | Qty | Provided by Uni? | Priority | Status | Unit cost | Total cost | Supplier / Link | Notes | Ordered | 1
TL071 op-amp (DIP-8) | 1 | Yes | High | Received | 0 | 0 |  |  | Received | 5
OPA551 op-amp (DIP-8) | 1 | Yes | High | To Get | 0 | 0 |  |  | Optional | 2
8 Ω speaker (enclosure preferred) | 1 | No | High | To Buy | 5 | 5
3.5 mm stereo jack socket | 100% | Yes | High | To Get | 0 | 0
DC jack (12 V input) | 1 | Yes | Medium | To Get | 0 | 0
PP3 9 V battery clip (optional) | 1 | Yes | Low | Optional | 0 | 0
On/off switch | 1 | Yes | High | To Get | 0 | 0
Power LED (5 mm) + resistor | 1 | Yes | Medium | To Get | 0 | 0
Potentiometer (volume control) | 1 | Yes | Medium | To Get | 0 | 0
Assorted resistors (E24) pack | 1 | Yes | Medium | Received | 0 | 0
Assorted capacitors (ceramic/film/electrolytic) | 1 | Yes | Medium | Received | 0 | 0
Perfboard/breadboard + jumper wires | 1 | Yes | Low | Received | 0 | 0 |  |  | Cost | £
Base plate / mounting hardware | 1 | Yes | Medium | Received | 0 | 0 |  |  | Received | 1
Enclosure / case materials | 1 | No | Low | Optional | 3 | 3 |  |  | Outstanding | 1
PCB fabrication (if charged) | 1 | No | High | Ordered | 0 | 0

## REPORT BREAKDOWN
REPORT BREAKDOWN • WRITING PROGRESS
Tick off report sections as you write. Status and % complete drive the dashboard.
Overall report completion | 0% | [5 empty] | 0%
Section | Brief requirement | Where covered (page/fig/table) | Status | Manual % (optional) | % Complete (auto) | Notes | Weight (marks) | Completion by section
Introduction | Title, abstract (~50–80 words), introduction (2–3 paragraphs). | Sec 1 | Not Started |  | 0% |  | 10%
Technical Background | Theory: bandpass filter, TL071 features, OPA551 features, key equations, references. | Sec 2 | Not Started |  | 0% |  | 25%
Design Description | Specs table, block diagram, detailed circuit design + calculations, component choices. | Sec 3 | Not Started |  | 0% |  | 20%
PCB Design | PCB layout screenshots, rules/placement/routing, 3D view, connectors & dimensions. | Sec 4 | Not Started |  | 0% |  | 10%
Results | Measured + simulated plots on same graph, test method, evaluation, assembly evidence. | Sec 5 | Not Started |  | 0% |  | 25%
References | Consistent IEEE references, cited in text, range of sources. | Sec 6 | Not Started |  | 0% |  | 8%
Appendices | BOM + full schematic, additional screenshots/data. | Appx | Not Started |  | 0% |  | 2%

## DESIGN & NOTES
DESIGN / NOTES
Capture design assumptions, key decisions, and build/testing checkpoints.
Key checkpoints |  |  | Design assumptions / decisions (keep it short and dated)
Simulation complete? | Not Started | AC sweep + transient verified | • Target Vout, Vpp: • Measured Vin at 70% volume: • Chosen gain + resistor rounding: • Chosen cut-offs (fl, fu) + capacitor rounding: • Power supply choice (9V battery vs 12V DC): • Any constraints / issues:
Schematic complete? | Not Started | All values + decoupling + connectors
PCB complete? | Not Started | DRC clean + placement/routing done
Build complete? | Not Started | Breadboard + PCB assembled
Evidence checklist (helps the report)
Photos: breadboard build | Not Started
Photos: PCB before solder | Not Started
Photos: PCB after solder | Not Started
Screenshots: Proteus frequency response | Not Started
Screenshots: Proteus transient (440 Hz) | Not Started
Screenshots: oscilloscope results | Not Started
Excel plots exported for report | Not Started
Quick links
Go to DASHBOARD | Open DASHBOARD
Go to GANTT | Open GANTT
Go to BOM | Open BOM
Go to REPORT BREAKDOWN | Open REPORT BREAKDOWN

## _Lists (hidden)
Global Status | Default % | Color (ARGB) | BOM Status | Color (ARGB) | Provided by Uni? | Color (ARGB) | Priority | Color (ARGB) | Default Weights | Weight
Not Started | 0 | FFE9ECEF | To Get | FFE9ECEF | Yes | FFE6FCF5 | High | FFFADBD8 | Engineering | 0.55
In Progress | 50 | FFF1C40F | To Buy | FFFFE5D0 | No | FFE9ECEF | Medium | FFFFF3CD | Report | 0.35
Done | 100 | FF27AE60 | Ordered | FFFFF3CD |  |  | Low | FFE9ECEF | BOM | 0.1
Blocked | 0 | FFE74C3C | Received | FFE6FCF5
Optional | 0 | FFD7BDE2 | Optional | FFD7BDE2