## Dashboard
AUDIO AMPLIFIER PROJECT WORKBOOK
Live tracker + Gantt + BOM + design calculations
Project window: 19 Jan 2026 to 13 Feb 2026
How to use: Update task dates & % complete in the Gantt sheet. Update purchase/received status in the BOM sheet. Dashboard updates automatically.
Overall progress (%) | 17.45%
Days remaining | 22
Tasks complete | 4
Key sign-offs / deliverables (from project guidance)
Deliverable | Planned date | Status | Notes
Final schematic check
Final PCB check
PCB soldering check
Final test & measurement
Final audio check using speaker
Report draft complete
Final report submitted

## Gantt
PROJECT GANTT CHART (LIVE)
Edit Start/End/% Complete — bars update automatically
19 Jan 2026 to 13 Feb 2026 (weekdays shown)
Overall % (duration-weighted) | [11 empty] | 17.45% | 0.17451
Tip: Keep tasks small (1–3 days). Use Status + %Complete. For milestones set Start=End. | [10 empty] | Tasks done | 4 | 4
ID | Task | Category | Owner | Start | End | Duration (wd) | % Complete | Status | Dependencies | Notes | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13
[11 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
T01 | Read brief + rubric + set up workbook | Planning | Zac | 2026-01-19 | 2026-01-19 | 1 | 100% | Done |  | Set up files / plan
T02 | Week 3 self-study: TL071/OPA551 datasheets + active bandpass videos | Planning | Zac | 2026-01-19 | 2026-01-20 | 2 | 100% | Done
T03 | Mobile phone characterisation (440 Hz Vpp vs volume) | Measurements | Zac | 2026-01-20 | 2026-01-21 | 2 | 100% | Done
T04 | Design calculations in Excel (gain, R1/R2, C1/C2, decoupling) | Design | Zac | 2026-01-21 | 2026-01-23 | 3 | 100% | Done | T03 | Use Design Calculations sheet
T05 | Proteus sim (dual supply): AC sweep + transient @ 440 Hz | Simulation | Zac | 2026-01-23 | 2026-01-27 | 3 | 30% | In Progress | T04 | Capture plots for report
M01 | Sign-off: Final schematic check | Milestone | Zac | 2026-01-27 | 2026-01-27 | 1 | 0% | Not Started | T05
T06 | Breadboard build (dual supply) + measurements | Lab build/test | Zac | 2026-01-28 | 2026-01-30 | 3 | 0% | Not Started | M01 | Freq response + gain check
T07 | Single-supply bias design + update schematic | Design | Zac | 2026-01-30 | 2026-02-02 | 2 | 0% | Not Started | T06 | Bias network + AC coupling
T08 | Proteus sim (single supply): stability + clipping check | Simulation | Zac | 2026-02-02 | 2026-02-04 | 3 | 0% | Not Started | T07
T09 | Breadboard build (single supply) + measurements | Lab build/test | Zac | 2026-02-04 | 2026-02-06 | 3 | 0% | Not Started | T08
T10 | Order / collect remaining parts (switch, LED, connectors, speaker/enclosure, power) | Procurement | Zac | 2026-02-04 | 2026-02-06 | 3 | 0% | Not Started
T11 | PCB layout in Proteus + DRC | PCB | Zac | 2026-02-06 | 2026-02-10 | 3 | 0% | Not Started | T09 | Include mounting holes
M02 | Sign-off: Final PCB check | Milestone | Zac | 2026-02-10 | 2026-02-10 | 1 | 0% | Not Started | T11
T12 | PCB manufacture / print / prep (depends on process) | PCB | Zac | 2026-02-10 | 2026-02-12 | 3 | 0% | Not Started | M02
M03 | Sign-off: PCB soldering check | Milestone | Zac | 2026-02-12 | 2026-02-12 | 1 | 0% | Not Started | T12
T13 | Final assembly on base plate + wiring tidy + strain relief | Assembly | Zac | 2026-02-12 | 2026-02-13 | 2 | 0% | Not Started | M03
M04 | Sign-off: Final test & measurement | Milestone | Zac | 2026-02-13 | 2026-02-13 | 1 | 0% | Not Started | T13
M05 | Sign-off: Final audio check using speaker | Milestone | Zac | 2026-02-13 | 2026-02-13 | 1 | 0% | Not Started | M04
T14 | Report writing: screenshots, plots, BOM, reflection | Report | Zac | 2026-01-28 | 2026-02-13 | 13 | 0% | Not Started |  | Keep within 15 pages

## BOM
BILL OF MATERIALS (BOM)
Includes university-provided and recommended purchased items
Update Qty, Provided?, Status, Supplier, and Cost
Tip: Mark Provided by Uni = Yes for items you collect from stock. Use Status to track buying. Total cost updates automatically.
Category | Component / Item | Specification / Value | Qty | Provided by Uni? | Supplier | Part No / Link | Unit Cost | Total Cost | Priority | Status | Notes
ICs | TL071 op-amp | DIP-8 (TL071CP equivalent) | 1 | Yes |  |  |  |  | High | To Get | Required for summing + band-pass
ICs | OPA551 power op-amp | DIP-8 (OPA551PA equivalent) | 1 | Yes |  |  |  |  | High | To Get | Required for speaker drive
Resistors | R1 (feedback) | 82 kΩ (MF25_82k) | 1 | Yes |  |  |  |  | High | To Get | From design calculations
Resistors | R2 (gain set) | 24 kΩ (MF25_24k) | 1 | Yes |  |  |  |  | High | To Get | From design calculations
Resistors | Stereo summing resistors (L & R) | 10 kΩ (typical) — confirm in schematic | 2 | Yes |  |  |  |  | High | To Get | Stops L/R outputs fighting
Resistors | Bias network resistors | 2× 47 kΩ (typical) — confirm | 2 | Yes |  |  |  |  | Med | To Get | For mid-supply reference
Capacitors | C1 (upper cut-off) | 68 pF ceramic (CER_68P) | 1 | Yes |  |  |  |  | High | To Get | From design calculations
Capacitors | C2 (lower cut-off) | 1 µF electrolytic (ELEC_1U) | 1 | Yes |  |  |  |  | High | To Get | From design calculations
Capacitors | Input coupling capacitor | 1–10 µF electrolytic — confirm | 1 | Yes |  |  |  |  | Med | To Get | Blocks DC into bias point
Capacitors | Decoupling caps | 100 nF (POLY_100N) | 4 | Yes |  |  |  |  | High | To Get | +V and -V for TL071 & OPA551
Capacitors | Bulk decoupling caps | 10 µF (ELEC_10U) | 2 | Yes |  |  |  |  | Med | To Get | Near OPA551 supply pins
Connectors | 3.5 mm stereo input jack | Panel mount TRS (stereo) | 1 | No |  |  |  |  | High | To Buy | Phone input
Power | 9 V PP3 battery | Alkaline | 1 | No |  |  |  |  | Med | To Buy | If using battery power
Power | 9 V PP3 battery clip/holder | Leads or panel holder | 1 | No |  |  |  |  | Med | To Buy
Power | 12 V DC adapter | Regulated, centre-positive (suggest 1 A) | 1 | No |  |  |  |  | Med | To Buy | If using DC supply
Power | DC barrel jack | Panel mount, matches adapter | 1 | No |  |  |  |  | Med | To Buy
UI | On/off switch | Toggle/rocker/slide, rated ≥1 A | 1 | No |  |  |  |  | High | To Buy | Required by brief
UI | Power indicator LED | 5 mm (any colour) + bezel | 1 | No |  |  |  |  | High | To Buy | Required by brief
Resistors | LED resistor | ~1 kΩ (depends on LED + supply) | 1 | Yes |  |  |  |  | High | To Get | Set after choosing supply voltage
Audio | Speaker | 8 Ω, 3–5 W (recommended) | 1 | No |  |  |  |  | High | To Buy | Better sound and safer load
Audio | Speaker enclosure (optional) | Small box or ready-made enclosure | 1 | No |  |  |  |  | Low | Optional | Improves audio a lot
Build | Base plate / mounting | Uni-provided base mount + standoffs | 1 | Yes |  |  |  |  | High | To Get | Must mount securely
Build | Hook-up wire | Solid core + stranded | 1 | No |  |  |  |  | Med | To Buy
Build | Heatshrink + cable ties | Assorted | 1 | No |  |  |  |  | Low | Optional | Neatness + strain relief
Build | Screws + standoffs | M3 assorted kit | 1 | No |  |  |  |  | Low | Optional | Secure mounting
Build | Terminal block / speaker connector | 2-way | 1 | No |  |  |  |  | Low | Optional | Easier assembly
Thermal | Small heatsink (optional) | Clip-on for DIP-8 or aluminium tab sink | 1 | No |  |  |  |  | Low | Optional | If OPA551 runs warm
Estimated total cost | [6 empty] | Total | 0

## Report Breakdown
REPORT BREAKDOWN (Parts B, D, E)
Mapping to report sections + build/marking checklist + ordering placeholder
Use: Copy/paste into report planning. Update if your design changes.
Tip: This sheet is static notes/checklists. Your live schedule is in the Gantt sheet. Your parts list is in the BOM sheet.
B - Map each requirement to report sections
| Brief requirement | Where I cover it in my report
| Power requirement (9 V or 12 V) | Power supply design and biasing strategy, decoupling
| Base plate mounting | Mechanical construction, photos, safety and wiring
| On/off switch and power LED | User interface, schematic snippet, LED resistor choice
| TL071 summing and filtering | Signal processing stage, calculations, frequency response plot
| OPA551 speaker driver | Power stage design, load considerations, output swing checks
| University provided components | Bill of materials, stock part selection
| Reuse and sustainability | Design considerations and sustainability notes
| Keep device after marking | Conclusion, reflection, portfolio value
D - Build and marking checklist
Electrical
| • | Stereo inputs summed safely (L + R) using resistors into the TL071 summing node
| • | Active band-pass filter meets my target cut-offs after rounding to stock parts
| • | Mid-band gain meets target output without clipping
| • | OPA551 configured to provide current drive into an 8 Ω speaker load
| • | Power supply decoupling fitted close to IC pins
Mechanical
| • | PCB or board securely fixed to the base plate
| • | Speaker securely fixed and wired safely
| • | Battery holder or DC jack securely fixed
| • | Wiring tidy, strain relieved, and labelled where needed
User
| • | On/off switch is accessible and clearly labelled
| • | Power LED is visible and current limited
Documentation
| • | Excel sheets saved and referenced
| • | Proteus plots and screenshots captured
| • | Photos taken at key build stages
| • | Final block diagram included
E - Items I might need to order (placeholder)
I will fill this after deciding my final build choices. Typical items include: power option (battery holder or DC adapter), switch, LED parts, speaker, and enclosure hardware. See the BOM sheet to track ordering.

## MB Phone Characterisation
Volume (Steps 1-16) | Vpp(440Hz) | Vpp(440Hz) - Simplified [V] | Abs diff to 70% target | 70% Point (Step) | 70% Target Vpp [V] | Chosen step Vpp [V] | Error (Chosen - Target) [V] | % Error | Source and test conditions |  | X (70% line and chosen point) | Y [V] (70% line and chosen point)
1 | 48.00mV | 0.048 | 0.8088 | 15 | 0.8568 | 0.872 | 0.0152 | 1.774% | Source device | iPhone 14 Pro Max | 1 | 0.8568
2 | 48.00mV | 0.048 | 0.8088 | [5 empty] | Test tone frequency [Hz] | 440 | 16 | 0.8568
3 | 48.00mV | 0.048 | 0.8088 | [5 empty] | Volume scale | Steps 1 to 16
4 | 48.00mV | 0.048 | 0.8088 | [5 empty] | Chosen design point | 70% of max Vpp | 15 | 0.872
5 | 48.00mV | 0.048 | 0.8088 | [5 empty] | Max measured Vpp [V] | 1.224
6 | 48.00mV | 0.048 | 0.8088 | [5 empty] | 70% target Vpp [V] | 0.8568
7 | 56.00mV | 0.056 | 0.8008 | [5 empty] | Closest volume step / Chosen design volume setting | Step 15
8 | 72.00mV | 0.072 | 0.7848 | [5 empty] | Chosen step Vpp [V] | 0.872
9 | 104.0mV | 0.104 | 0.7528 | [5 empty] | Error (Chosen - Target) [V] | 0.0152
10 | 152.0mV | 0.152 | 0.7048 | [5 empty] | Percent error | 1.774%
11 | 208.0mV | 0.208 | 0.6488 | [5 empty] | Chosen step Vrms [V] | 0.3083
12 | 320.0mV | 0.32 | 0.5368 | [5 empty] | Vin (chosen step) Vpp [V] | 0.872
13 | 448.0mV | 0.448 | 0.4088 | [5 empty] | Vin (chosen step) Vrms [V] | 0.3083
14 | 624.0mV | 0.624 | 0.2328
15 | 872.0mV | 0.872 | 0.0152
16 | 1.224V | 1.224 | 0.3672

## Design Calculations
Names / Parameters | Values | Units | Real component name (Proteus Aston name)
Phone input values (rows 3–6)
Max phone Vpp | 1.224 | V
0.7 phone Vpp target | 0.8568 | V
Chosen design Vin Vpp | 0.872 | V
Chosen design Vin Vrms | 0.3083 | V
Gain / resistor results (rows 8–16)
Target Vout Vpp (spec) | 3 | V
Required gain (V/V) | 3.4404 | V/V
Required gain (dB) | 10.7321 | dB
R1 (given feedback) | 82000 | Ohms | MF25_82k
R2 calculated (input) | 23834.6667 | Ohms
R2 rounded (chosen) | 24000 | Ohms | MF25_24k
Actual gain (using rounded R2) | 3.4167 | V/V
Actual gain (dB) | 10.6721 | dB
Lower cut-off section (rows 18–21)
Lower cut-off frequency fl (given) | 5 | Hz
C2 calculated | 1.3263e-06 | F
C2 rounded (chosen) | 1e-06 | F | ELEC_1U
Actual fl | 6.6315 | Hz
Upper cut-off section (rows 23–26)
Upper cut-off frequency fu (chosen) | 29000 | Hz
C1 calculated | 6.6928e-11 | F
C1 rounded (chosen) | 6.8e-11 | F | CER_68P
Actual fu | 28542.8521 | Hz
Decoupling caps (rows 28–35)
C+ decouple (TL071 +V to 0V) | 1e-07 | F | POLY_100N
C- decouple (TL071 -V to 0V) | 1e-07 | F | POLY_100N
OPA551 decouple +V to 0V | 1e-07 | F | POLY_100N
OPA551 decouple -V to 0V | 1e-07 | F | POLY_100N
OPA551 bulk +V to 0V | 1e-05 | F | ELEC_10U
OPA551 bulk -V to 0V | 1e-05 | F | ELEC_10U