## Dashboard
AUDIO AMPLIFIER PROJECT WORKBOOK
Live tracker + Gantt + BOM + design calculations
Project window: 19 Jan 2026 to 20 Feb 2026
How to use: Update task dates & % complete in the Gantt sheet. Update purchase/received status in the BOM sheet. Dashboard updates automatically.
[5 empty] | Task Status | Count
Overall progress (%) | 100% |  |  |  | Not Started | 0
Days remaining | 0 |  |  |  | In Progress | 0
Tasks complete | 20 |  |  |  | Done | 20
[5 empty] | Blocked | 0
Key sign-offs / deliverables (from project guidance)
Deliverable | Planned date | Status | Notes | % Complete
Final schematic check | 2026-01-27 | Done | Schematic DRC passed, all components correct | 100%
Final PCB check | 2026-02-10 | Done | DRC 0 errors, track widths T30/T40 confirmed | 100%
PCB soldering check | 2026-02-14 | Done | All components soldered, visual inspection passed | 100%
Final test & measurement | 2026-02-17 | Done | Freq response, gain and waveform measurements complete | 100%
Final audio check | 2026-02-17 | Done | 440 Hz tone audible through 8 Ω speaker, no distortion | 100%
Report draft complete | 2026-02-28 | Done | All sections written, figures and references complete | 100%
Final report submitted | 2026-03-03 | Done | Submitted to Blackboard as attempt 2 PDF | 100%
[5 empty] | Date | Planned done | Actual done
Recommendations (so this stays smooth in Week 3–7) |  |  |  |  | 2026-01-19 | 1 | 1
• Lock in your power plan early (9V vs 12V). Then choose switch, LED resistor, and connector to match. |  |  |  |  | 2026-01-20 | 2 | 2
• Treat decoupling as 'non‑negotiable' (100 nF right next to each op‑amp supply pin) to avoid oscillation. |  |  |  |  | 2026-01-21 | 3 | 3
• Use an 8 Ω speaker in an enclosure if possible — it’s the biggest improvement for perceived audio quality. |  |  |  |  | 2026-01-26 | 4 | 4
• Do one AC sweep + one 440 Hz transient in Proteus for each major change, then export plots to Excel for the report. |  |  |  |  | 2026-01-27 | 6 | 6
• Photograph each build stage (breadboard → PCB → final assembly) so the report is easy to write. |  |  |  |  | 2026-01-28 | 6 | 6
[5 empty] | 2026-01-29 | 6 | 6
[5 empty] | 2026-01-30 | 7 | 7
[5 empty] | 2026-02-02 | 8 | 8
[5 empty] | 2026-02-03 | 8 | 8
[5 empty] | 2026-02-04 | 9 | 9
[5 empty] | 2026-02-05 | 9 | 9
[5 empty] | BOM Status | Count | 0
[5 empty] | To Get | 1 | 0
[5 empty] | To Buy | 2 | 0
[5 empty] | Ordered | 0 | 0
[5 empty] | Received | 19 | 0
[5 empty] | Optional | 5 | 0

## Gantt
PROJECT GANTT CHART (LIVE)
Edit Start/End/% Complete — bars update automatically
19 Jan 2026 to 20 Feb 2026 (weekdays shown)
| Overall % (duration-weighted) | [10 empty] | 100% | 100% | Status | Count
Tip: Keep tasks small (1–3 days). Use Status + %Complete. For milestones set Start=End. | [10 empty] | Tasks done | 20 | 20 | Not Started | 0
[14 empty] | In Progress | 0
ID | Task | Category | Owner | Start | End | Duration (wd) | % Complete | Status | Dependencies | Notes | 2026-01-19 | 2026-01-20 | 2026-01-21 | Done | 1900-01-19 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20
[11 empty] | Mon | Tue | Wed | Blocked | 0 | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
T01 | Read brief + rubric + set up workbook | Planning | Zac | 2026-01-19 | 2026-01-19 | 1 | 100% | Done |  | Set up files / plan
T02 | Week 3 self-study: TL071/OPA551 datasheets + active bandpass videos | Planning | Zac | 2026-01-19 | 2026-01-20 | 2 | 100% | Done
T03 | Mobile phone characterisation (440 Hz Vpp vs volume) | Measurements | Zac | 2026-01-20 | 2026-01-21 | 2 | 100% | Done
T04 | Design calculations in Excel (gain, R1/R2, C1/C2, decoupling) | Design | Zac | 2026-01-21 | 2026-01-23 | 3 | 100% | Done | T03 | Use Design Calculations sheet
T05 | Proteus sim (dual supply): AC sweep + transient @ 440 Hz | Simulation | Zac | 2026-01-23 | 2026-01-27 | 3 | 100% | Done | T04 | Capture plots for report
M01 | Sign-off: Final schematic check | Milestone | Zac | 2026-01-27 | 2026-01-27 | 1 | 100% | Done | T05
T06 | Breadboard build (dual supply) + measurements | Lab build/test | Zac | 2026-01-28 | 2026-01-30 | 3 | 100% | Done | M01 | Freq response + gain check
T07 | Single-supply bias design + update schematic | Design | Zac | 2026-01-30 | 2026-02-02 | 2 | 100% | Done | T06 | Bias network + AC coupling
T08 | Proteus sim (single supply): stability + clipping check | Simulation | Zac | 2026-02-02 | 2026-02-04 | 3 | 100% | Done | T07
T09 | Breadboard build (single supply) + measurements | Lab build/test | Zac | 2026-02-04 | 2026-02-06 | 3 | 100% | Done | T08
T10 | Order / collect remaining parts (switch, LED, connectors, speaker/enclosure, power) | Procurement | Zac | 2026-02-04 | 2026-02-06 | 3 | 100% | Done
T11 | PCB layout in Proteus + DRC | PCB | Zac | 2026-02-06 | 2026-02-10 | 3 | 100% | Done | T09 | Include mounting holes
M02 | Sign-off: Final PCB check | Milestone | Zac | 2026-02-10 | 2026-02-10 | 1 | 100% | Done | T11
T12 | PCB manufacture / print / prep (depends on process) | PCB | Zac | 2026-02-10 | 2026-02-13 | 4 | 100% | Done | M02
M03 | Sign-off: PCB soldering check | Milestone | Zac | 2026-02-14 | 2026-02-14 | 0 | 100% | Done | T12
T13 | Final assembly on base plate + wiring tidy + strain relief | Assembly | Zac | 2026-02-14 | 2026-02-17 | 2 | 100% | Done | M03
M04 | Sign-off: Final test & measurement | Milestone | Zac | 2026-02-17 | 2026-02-17 | 1 | 100% | Done | T13
M05 | Sign-off: Final audio check using speaker | Milestone | Zac | 2026-02-17 | 2026-02-17 | 1 | 100% | Done | M04
T14 | Report writing: screenshots, plots, BOM, reflection | Report | Zac | 2026-01-28 | 2026-03-03 | 25 | 100% | Done |  | Keep within 15 pages
M06 | Sign-off: Final report submitted | Milestone | Zac | 2026-03-03 | 2026-03-03 | 1 | 100% | Done | T14 | Submit on Blackboard

## BOM
BILL OF MATERIALS (BOM)
Includes university-provided and recommended purchased items
Update Qty, Provided?, Status, Supplier, and Cost
Tip: Mark Provided by Uni = Yes for items you collect from stock. Use Status to track buying. Total cost updates automatically.
Category | Component / Item | Specification / Value | Qty | Provided by Uni? | Supplier | Part No / Link | Unit Cost | Total Cost | Priority | Status | Notes
ICs | TL071 op-amp | TL071CP, DIP-8 | 1 | Yes | Aston MB252 | TL071CP | 0 | 0 | High | Received | U1 — inverting summing active BPF stage
ICs | OPA551 power op-amp | OPA551PA, DIP-8 | 1 | Yes | Aston MB252 | OPA551PA | 0 | 0 | High | Received | U2 — unity-gain current buffer, speaker driver
Resistors | R1 (feedback) | 82 kΩ, 0.25W metal film | 1 | Yes | Aston MB252 | MF25_82k | 0 | 0 | High | Received | Sets upper end of gain ratio
Resistors | R2, R3, R4, R5 (gain + bias) | 24 kΩ, 0.25W metal film ×4 | 4 | Yes | Aston MB252 | MF25_24k | 0 | 0 | High | Received | R2=gain set; R3/R4=bias divider; R5=summing
Resistors | R6 (LED current limit) | 3.3 kΩ, 0.25W metal film | 1 | Yes | Aston MB252 | MF25_3k3 | 0 | 0 | High | Received | Limits LED current on 12V supply
Resistors | R7 (simulation load) | 8.2 Ω, 0.25W metal film | 1 | Yes | Aston MB252 | MF25_8R2 | 0 | 0 | Med | Received | Proteus speaker substitute; not on final PCB speaker output
Capacitors | C1 (upper cut-off) | 68 pF ceramic | 1 | Yes | Aston MB252 | CER_68P | 0 | 0 | High | Received | Sets fH = 28.54 kHz with R1
Capacitors | C2, C6 (lower cut-off + input coupling) | 1 µF electrolytic ×2 | 2 | Yes | Aston MB252 | ELEC_1U | 0 | 0 | High | Received | C2 sets fL = 6.63 Hz; C6 AC input coupling
Capacitors | C3, C4, C7 (decoupling) | 100 nF polyester film ×3 | 3 | Yes | Aston MB252 | POLY_100N | 0 | 0 | High | Received | Supply decoupling on U1 and U2 pins
Capacitors | C5 (bulk decoupling) | 10 µF electrolytic | 1 | Yes | Aston MB252 | ELEC_10U | 0 | 0 | Med | Received | Bulk decoupling near OPA551 supply
Capacitors | C8 (output coupling) | 2200 µF electrolytic | 1 | Yes | Aston MB252 | ELEC_2200U | 0 | 0 | High | Received | DC blocks output; fC = 9.05 Hz with 8 Ω load
Diodes | D1 (power LED) | Green 5mm LED | 1 | Yes | Aston MB252 | LED-GREEN_A | 0 | 0 | High | Received | Power-on indicator
Diodes | D2, D3 (reverse polarity protection) | 1N4007 rectifier diode ×2 | 2 | Yes | Aston MB252 | 1N4007 | 0 | 0 | High | Received | Reverse polarity protection on supply rails
Connectors | J1 (stereo input jack) | 3.5mm stereo PCB jack socket | 1 | Yes | Aston MB252 | JACK SOCKET | 0 | 0 | High | Received | iPhone audio input
Connectors | J2 (speaker terminal block) | 2-way 5.08mm terminal block | 1 | Yes | Aston MB252 | TBLOCK-I2 | 0 | 0 | High | Received | Speaker output connection
Audio | LS1 (speaker) | 8 Ω speaker | 1 | Yes | Aston MB252 | SPEAKER_A | 0 | 0 | High | Received | Load for OPA551 output stage
UI | SW1 (on/off switch) | PCB-mount SPST slide switch | 1 | Yes | Aston MB252 | SLIDE-SPST_A | 0 | 0 | High | Received | Required by brief — power on/off
Test Points | TP1–TP5 (test pins) | Test pin ×5 | 5 | Yes | Aston MB252 | TEST_PIN | 0 | 0 | Med | Received | TP1=Bias, TP2=Stage1, TP3=Power, TP4=GND, TP5=Test
Build | Base plate + standoffs | 3mm acrylic baseplate, M3 nylon standoffs | 1 | Yes | Aston MB252 | N/A | 0 | 0 | High | Received | PCB mounted at 4 corners with M3 nylon standoffs
Audio | Speaker | 8 Ω, 3–5 W (recommended) | 1 | No |  |  |  | 0 | High | To Buy | Better sound and safer load
Audio | Speaker enclosure (optional) | Small box or ready-made enclosure | 1 | No |  |  |  | 0 | Low | Optional | Improves audio a lot
Build | Base plate / mounting | Uni-provided base mount + standoffs | 1 | Yes |  |  |  | 0 | High | To Get | Must mount securely
Build | Hook-up wire | Solid core + stranded | 1 | No |  |  |  | 0 | Med | To Buy
Build | Heatshrink + cable ties | Assorted | 1 | No |  |  |  | 0 | Low | Optional | Neatness + strain relief
Build | Screws + standoffs | M3 assorted kit | 1 | No |  |  |  | 0 | Low | Optional | Secure mounting
Build | Terminal block / speaker connector | 2-way | 1 | No |  |  |  | 0 | Low | Optional | Easier assembly
Thermal | Small heatsink (optional) | Clip-on for DIP-8 or aluminium tab sink | 1 | No |  |  |  | 0 | Low | Optional | If OPA551 runs warm
Estimated total cost | [6 empty] | Total | 0

## Report Breakdown
REPORT BREAKDOWN (Parts B, D, E)
Mapping to report sections + build/marking checklist + ordering placeholder
Use: Copy/paste into report planning. Update if your design changes.
Tip: This sheet is static notes/checklists. Your live schedule is in the Gantt sheet. Your parts list is in the BOM sheet.
|  |  | Overall completion | 95.83%
B - Map each requirement to report sections
| Brief requirement | Where I cover it in my report | Status |  | Report section | Status score
| Power requirement (9 V or 12 V) | Power supply design and biasing strategy, decoupling | Done |  | Power requirement (9 V or 12 V) | 100%
| Base plate mounting | Mechanical construction, photos, safety and wiring | Done |  | Base plate mounting | 100%
| On/off switch and power LED | User interface, schematic snippet, LED resistor choice | Done |  | On/off switch and power LED | 100%
| TL071 summing and filtering | Signal processing stage, calculations, frequency response plot | Done |  | TL071 summing and filtering | 100%
| OPA551 speaker driver | Power stage design, load considerations, output swing checks | Done |  | OPA551 speaker driver | 100%
| University provided components | Bill of materials, stock part selection | Done |  | University provided components | 100%
| Reuse and sustainability | Design considerations and sustainability notes | Done |  | Reuse and sustainability | 100%
| Keep device after marking | Conclusion, reflection, portfolio value | Done |  | Keep device after marking | 100%
D - Build and marking checklist
| Electrical |  | Status |  | Section | % Complete
| • | Stereo inputs summed safely (L + R) using resistors into the TL071 summing node | Done |  | Electrical | 100%
| • | Active band-pass filter meets my target cut-offs after rounding to stock parts | Done |  | Mechanical | 100%
| • | Mid-band gain meets target output without clipping | Done |  | User | 100%
| • | OPA551 configured to provide current drive into an 8 Ω speaker load | Done |  | Documentation | 100%
| • | Power supply decoupling fitted close to IC pins | Done
Mechanical
| • | PCB or board securely fixed to the base plate | Done
| • | Speaker securely fixed and wired safely | Done
| • | Battery holder or DC jack securely fixed | Done
| • | Wiring tidy, strain relieved, and labelled where needed | Done
User
| • | On/off switch is accessible and clearly labelled | Done
| • | Power LED is visible and current limited | Done
Documentation
| • | Excel sheets saved and referenced | Done
| • | Proteus plots and screenshots captured | Done
| • | Photos taken at key build stages | Done
| • | Final block diagram included | Done
E - Items ordered / acquired for build
All components were sourced from Aston University MB252 stock (Richard Reeves). Items collected: TL071CP, OPA551PA, MF25 resistors (82k, 24k×4, 3k3, 8R2), CER_68P, ELEC_1U×2, POLY_100N×3, ELEC_10U, ELEC_2200U, LED-GREEN_A, 1N4007×2, JACK SOCKET, TBLOCK-I2, SPEAKER_A, SLIDE-SPST_A, TEST_PIN×5, base plate and M3 nylon standoffs. No external purchases were required. All items received prior to PCB assembly.

## MB Phone Characterisation
Volume (Steps 1-16) | Vpp(440Hz) | Vpp(440Hz) - Simplified [V] | Abs diff to 70% target | 70% Point (Step) | 70% Target Vpp [V] | Chosen step Vpp [V] | Error (Chosen - Target) [V] | % Error | Source and test conditions |  | X (70% line and chosen point) | Y [V] (70% line and chosen point)
1 | 48.00mV | 0.048 | 0.8088 | 15 | 0.8568 | 0.872 | 0.0152 | 1.774% | Source device | iPhone 14 Pro Max | 1 | 0.8568
2 | 48.00mV | 0.048 | 0.8088 | [5 empty] | Test tone frequency [Hz] | 440 | 16 | 0.8568
3 | 48.00mV | 0.048 | 0.8088 | [5 empty] | Volume scale | Steps 1 to 16
4 | 48.00mV | 0.048 | 0.8088 | [5 empty] | Chosen design point | 70% of max Vpp | 15 | 0.872
5 | 48.00mV | 0.048 | 0.8088 | [5 empty] | Max measured Vpp [V] | 1.224
6 | 48.00mV | 0.048 | 0.8088 | [5 empty] | 70% target Vpp [V] | 0.8568
7 | 56.00mV | 0.056 | 0.8008 | [5 empty] | Closest volume step / Chosen design volume setting | Step 15
8 | 72.00mV | 0.072 | 0.7848 | [5 empty] | Chosen step Vpp [V] | 0.872
9 | 104.0mV | 0.104 | 0.7528 | [5 empty] | Error (Chosen - Target) [V] | 0.0152
10 | 152.0mV | 0.152 | 0.7048 | [5 empty] | Percent error | 1.774%
11 | 208.0mV | 0.208 | 0.6488 | [5 empty] | Chosen step Vrms [V] | 0.3083
12 | 320.0mV | 0.32 | 0.5368 | [5 empty] | Vin (chosen step) Vpp [V] | 0.872
13 | 448.0mV | 0.448 | 0.4088 | [5 empty] | Vin (chosen step) Vrms [V] | 0.3083
14 | 624.0mV | 0.624 | 0.2328
15 | 872.0mV | 0.872 | 0.0152
16 | 1.224V | 1.224 | 0.3672

## Design Calculations
Names / Parameters | Values | Units | Real component name (Proteus Aston name)
Phone input values (rows 3–6)
Max phone Vpp | 1.224 | V
0.7 phone Vpp target | 0.8568 | V
Chosen design Vin Vpp | 0.872 | V
Chosen design Vin Vrms | 0.3083 | V
Gain / resistor results (rows 8–16)
Target Vout Vpp (spec) | 3 | V
Required gain (V/V) | 3.4404 | V/V
Required gain (dB) | 10.7321 | dB
R1 (given feedback) | 82000 | Ohms | MF25_82k
R2 calculated (input) | 23834.6667 | Ohms
R2 rounded (chosen) | 24000 | Ohms | MF25_24k
Actual gain (using rounded R2) | 3.4167 | V/V
Actual gain (dB) | 10.6721 | dB
Lower cut-off section (rows 18–21)
Lower cut-off frequency fl (given) | 5 | Hz
C2 calculated | 1.3263e-06 | F
C2 rounded (chosen) | 1e-06 | F | ELEC_1U
Actual fl | 6.6315 | Hz
Upper cut-off section (rows 23–26)
Upper cut-off frequency fu (chosen) | 29000 | Hz
C1 calculated | 6.6928e-11 | F
C1 rounded (chosen) | 6.8e-11 | F | CER_68P
Actual fu | 28542.8521 | Hz
Decoupling caps (rows 28–35)
C+ decouple (TL071 +V to 0V) | 1e-07 | F | POLY_100N
C- decouple (TL071 -V to 0V) | 1e-07 | F | POLY_100N
OPA551 decouple +V to 0V | 1e-07 | F | POLY_100N
OPA551 decouple -V to 0V | 1e-07 | F | POLY_100N
OPA551 bulk +V to 0V | 1e-05 | F | ELEC_10U
OPA551 bulk -V to 0V | 1e-05 | F | ELEC_10U